## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
TA-001 | TA Account Registration | As a TA, I want to create an account, so that I can access the recruitment system. | Must Have | 1 | 1. User can register with name, email, and password 2. System validates email format 3. Password must meet security requirements 4. Can log in after successful registration | 5 | TA must use school email to register | 2026-03-23 | 2026-04-05
TA-002 | TA Login | As a TA, I want to log in to the system, so that I can access my profile and applications. | Must Have | 1 | 1. User can log in with email and password 2. Display error message on login failure 3. Support "Remember Me" status 4. Support password recovery via email verification | 3 | Password recovery function is required | 2026-03-23 | 2026-04-05
TA-003 | TA Profile Creation | As a TA, I want to create my applicant profile, so that MOs can view my qualifications | Must Have | 1 | 1. Can fill in personal info (name, major, grade) 2. Can add skill tags 3. Can enter available working hours 4. Profile can be saved and edited | 5 | Fill in basic personal info based on the existing recruitment questionnaire | 2026-03-23 | 2026-04-05
TA-004 | TA Browse Available Courses | As a TA, I want to browse available courses, so that I can quickly find courses that I may want to apply for. | Must Have | 2 | 1. Display list of all positions posted by MOs 2. Show course name, MO info, and recruitment quota 3. Can filter by course name, time, or requirements | 5 | - | 2026-04-06 | 2026-04-19
TA-005 | View Course Requirements | As a TA, I want to view detailed course requirements, so that I can assess whether I am qualified for the course. | Must Have | 2 | 1. Show specific requirements for each course, including skills and working hours 2. Provide MO info for each course 3. Show application deadline and headcount requirement | 5 | TA Interview: Currently unaware of specific requirements, required skills, or who is teaching; can only select blindly based on course name | 2026-04-06 | 2026-04-19
TA-006 | TA Apply for Positions (Max 3) | As a TA, I want to apply for multiple courses, so that I can choose positions that best match my interests and availability. | Must Have | 2 | 1. Click to apply for desired positions 2. Max 3 courses can be applied for 3. Status changes to "Pending Review" after applying 4. View application history 5. TA can cancel unprocessed applications 6. Can apply for other courses if rejected (total applications not exceeding 3) | 5 | Current recruitment process limits selection to a maximum of 3 positions | 2026-04-06 | 2026-04-19
TA-007 | TA Upload CV | As a TA, I want to upload my CV directly in the system, so that MOs can review my qualifications | Must Have | 2 | 1. Support PDF/Word format upload 2. File size limit check 3. Viewable in profile after successful upload 4. Support re-upload | 5 | TA Interview: Currently requires manual renaming of resume (Student ID + Name) and sending a separate email, which is very tedious | 2026-04-06 | 2026-04-19
TA-008 | TA Check Application Status & Feedback | As a TA, I want to check my application status with detailed feedback, so that I know the result of my applications | Must Have | 2 | 1. Display list of all applications 2. Status includes: Pending Review / Waitlisted / Accepted / Rejected 3. Notification visible when placed on waitlist 4. View result notification after MO's decision | 3 | TA Interview: Currently no feedback signal, just direct emails; want to see waitlist status | 2026-04-06 | 2026-04-19
TA-009 | TA Accept/Reject Offer | As a TA, I want to accept or reject offers through the system, so that MOs know my decision quickly | Must Have | 2 | 1. Can click accept/reject in the system after receiving an Offer 2. No need to reply via email 3. MO receives real-time notification 4. If rejected, TA is automatically released to other MOs | 5 | TA Interview: Currently replying accept/reject via email, process is cumbersome | 2026-04-06 | 2026-04-19
TA-010 | TA View Workload Records | As a TA, I want to view my workload records, so that I can track my working hours. | Should Have | 3 | 1. Display working hours for hired courses 2. Display total working hours | 3 | TA Interview: Currently workload is recorded via WeChat group messages, no system tracking | 2026-04-20 | 2026-05-03
MO-001 | MO Account Registration | As a MO, I want to create an account, so that I can manage TA recruitment for my module. | Must Have | 1 | 1. MO can register with work email 2. Requires Admin approval to activate account 3. Bind responsible courses after registration | 5 | MO must use school email to register | 2026-03-23 | 2026-04-05
MO-002 | MO Login | As a MO, I want to log in to the system, so that I can manage my recruitment tasks. | Must Have | 1 | 1. User can log in with email and password 2. Display error message on login failure | 3 | - | 2026-03-23 | 2026-04-05
MO-003 | MO Post Job Openings | As a MO, I want to post job openings with detailed requirements, so that TAs can understand what I need | Must Have | 2 | 1. Can enter course name 2. Can set required skills, recruitment headcount 3. Can set working hour requirements 4. Can set application deadline 5. Visible to TAs after posting 6. Can withdraw or edit posted job info | 5 | MO Interview: Will post skill requirements, working hours, start/end dates | 2026-04-06 | 2026-04-19
MO-004 | MO View Applicant List (Own Courses Only) | As a MO, I want to view ONLY applicants for my courses, so that I don't waste time on irrelevant applications. | Must Have | 2 | 1. Only display TAs applying for this MO's courses, hide applicants for other courses 2. Display in list format (not one person per page) 4. Can view TA profile and CV in the system | 5 | MO Interview: Only want to see applicants for own courses, not hundreds of applicants; want a list view, not flipping through 20 pages | 2026-04-06 | 2026-04-19
MO-005 | MO Review Applicants | As a MO, I want to review and decide on applicants, so that I can select the most suitable TAs efficiently. | Must Have | 2 | 1. Can click Accept / Reject / Waitlist for each applicant 2. Can add review remarks 3. TA receives system notification after review 4. Rejected TAs no longer appear in the list | 5 | - | 2026-04-06 | 2026-04-19
MO-006 | MO Send Offer via System | As a MO, I want to send offers through the system, so that I don't need to manually email each TA | Must Have | 2 | 1. One-click send Offer after selecting TA 2. No need to manually find email addresses to send emails 3. TA receives notification within the system 4. Supports batch sending | 5 | MO Interview: Currently, after finding a CV, still need to find the email and send notifications one by one, very tedious | 2026-04-06 | 2026-04-19
MO-007 | MO Handle Replacements (TA Rejections) | As a MO, I want to quickly find replacement TAs when selected TAs reject offers, so that I can fill positions efficiently. | Should Have | 3 | 1. MO is automatically notified if TA rejects Offer 2. Can quickly select the next candidate from the waitlist 3. No need to re-screen all applicants | 5 | MO Interview: If someone rejects, need to search again and send another email, all manual operations | 2026-04-20 | 2026-05-03
MO-008 | MO View Hired TAs & Contact Info | As a MO, I want to view my selected TAs with contact info, so that I can manage my team. | Should Have | 3 | 1. Display list of all accepted TAs 2. Can view TA contact information 3. Can export TA information | 3 | - | 2026-04-20 | 2026-05-03
MO-009 | MO Close Recruitment Window | As a MO, I want to close recruitment after deadline or when positions are filled, so that no more applications come in. | Should Have | 3 | 1. Can manually close recruitment positions 2. Auto-close after deadline 3. TAs cannot apply for the course after closing | 3 | MO Interview: There is a deadline, review all after deadline, close it when enough TAs are selected | 2026-04-20 | 2026-05-03
ADM-001 | Admin Login | As an Admin, I want to access the admin panel, so that I can manage the system. | Must Have | 1 | 1. Admin has an independent login portal 2. Default Admin account is preset by the system | 3 | Admin needs special permissions | 2026-03-23 | 2026-04-05
ADM-002 | Admin View All Data | As an Admin, I want to view recruitment data, so that I can monitor application progress and identify potential issues. | Should Have | 3 | 1. Can view all TA, MO, and position info 2. Can view all application records 3. Data displayed in table format, can be exported to Excel | 5 | - | 2026-04-20 | 2026-05-03
ADM-003 | Admin Manage Application Periods | As an Admin, I want to set global application periods, so that I can ensure recruitment happens within a controlled timeframe. | Should Have | 3 | 1. Admin can set global application start and end times 2. TAs cannot submit applications during global closed periods 3. MOs must set deadlines within the global timeframe when posting positions | 5 | - | 2026-04-20 | 2026-05-03
ADM-004 | Admin Manage User Accounts | As an Admin, I want to manage user accounts, so that I can activate/deactivate users | Should Have | 3 | 1. Can activate MO accounts 2. Can disable violating TA/MO accounts 3. Can reset user passwords | 5 | - | 2026-04-20 | 2026-05-03
SYS-001 | User Permission Management | As a user, I want the system to provide role-based access, so that I can only see features relevant to my role. | Must Have | 1 | 1. TA can only access TA features 2. MO can only access MO features 3. Admin can access all features | 5 | - | 2026-03-23 | 2026-04-05